## Production Release Checklist
PRODUCTION RELEASE CHECKLIST — lifestyle > lifestyle-new
Update the Status column as each task is completed. Filter by Owner / Priority as needed.
# | Area | Task | Details / Sub-tasks | Owner | Status | Priority | Target Date | Notes
1 | 1 · CC2 Change | Update RACKSPACE_LS_DIR | Change RACKSPACE_LS_DIR="lifestyle" → RACKSPACE_LS_DIR="lifestyle-new" | Dev Team | Not Started | Critical |  | New shoots go to lifestyle-new
2 | 1 · CC2 Change | Update concept container folder logic | $containerFolder = $concept == "max" ? "max-new" : $concept; | Dev Team | Not Started | Critical |  | Verify max folder separately
3 | 2 · Hybris IMPEX | IMPEX changes — all categories | Update image path references across all LS categories in IMPEX files | Jagnya | Not Started | Critical |  | Jagnay HS needs help on this
4 | 2 · Hybris AppConfig | V1 image URL update (UK) | image.storage.container.url.lifestyle.V1 https://media-uk.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnya | Not Started | High |  | UK CDN endpoint
5 | 2 · Hybris AppConfig | V2 image URL update (US) | image.storage.container.url.lifestyle.V2 https://media-us.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnya | Not Started | High |  | US CDN endpoint
6 | 2 · Hybris AppConfig | V3 image URL update (Global) | image.storage.container.url.lifestyle.V3 https://media.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnya | Not Started | High |  | Global CDN endpoint
7 | 2 · Hybris AppConfig | V4 image URL update (EA) | image.storage.container.url.lifestyle.V4 https://media-ea.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnay | Not Started | High |  | EA CDN endpoint
8 | 3 · Downstream | OMS — point to lifestyle-new container | OMS system container reference updated to lifestyle-new | Savitha Shivananda / Yeddulaharinath Reddy | Not Started | Critical
9 | 3 · Downstream | RMS — point to lifestyle-new container | RMS system container reference updated to lifestyle-new | Savitha Shivananda / Yeddulaharinath Reddy | Not Started | Critical
10 | 3 · Downstream | SAP — point to lifestyle-new container | SAP system container reference updated to lifestyle-new | Savitha Shivananda / Yeddulaharinath Reddy | Not Started | Critical
11 | 3 · Downstream | Cloudflare rules review | Check for any rules hard-coded to /lifestyle/; update to /lifestyle-new/ | Savitha Shivananda / Yeddulaharinath Reddy | Not Started | High
14 | 5 · Redis Cache | Clear Redis cache per category | Flush Redis after each LS category IMPEX run so PDP returns correct category | Dev / Infra Team | Not Started | Critical |  | Per-category, post each IMPEX
15 | 6 · QA Validation | Category pages — square images | Browse each LS category page; confirm product tiles render correctly | QA Team | Not Started | High |  | All categories must pass
16 | 7 · Cloudflare Cache | Purge Cloudflare cache — PDP Static API | Purge Cloudflare cache for all PDP static API responses to pick up new image URLs | Infra / DevOps | Not Started | Critical |  | Purge by tag or URL pattern
17 | 8 · Sanity Check | Gift card images working | Verify gift card product images load from lifestyle-new container | QA Team | Not Started | High
18 | 8 · Sanity Check | Elite product images working | Verify Elite product images load correctly from new container | QA Team | Not Started | High
19 | 8 · Sanity Check | Other assets (banners, icons) | Confirm non-product assets are unaffected by folder change | QA Team | Not Started | Medium
20 | 9 · Image Health | Run image health check script | python check-image-health.py --pages 0 --workers 100 Review broken_images.csv in image_health/ | Jagnya | Not Started | High |  | Run after all above steps done
21 | 9 · Image Health | Triage & action broken images | Review broken_images.csv; reprocess failed SKUs via reprocess_fill.py | Jagnya / Vishal Jaiswal | Not Started | High

## Legend
Status Legend
Not Started | Task has not been picked up yet
In Progress | Currently being worked on
Done | Completed and verified
Blocked | Blocked — needs escalation
Priority Legend
Critical | Go-live blocker — must complete before release
High | Important — complete before launch
Medium | Should complete; non-blocking
Low | Nice to have