## Release Checklist
Area | Task | Details | Owner | Status | Notes
CC2 Change | Update RACKSPACE_LS_DIR | RACKSPACE_LS_DIR="lifestyle" → RACKSPACE_LS_DIR="lifestyle-new" | Dev Team | Not Started
CC2 Change | Update concept folder logic | $containerFolder = $concept == "max" ? "max-new" : $concept; | Dev Team | Not Started
Hybris Deployment | Hybris Deployment | Hybris Deployment | Yeddulaharinath Reddy | Not Started
Hybris IMPEX | IMPEX changes — all categories | Update image path references across all LS categories | Jagnya / Vishal Jaiswal | Not Started
Hybris AppConfig | V1 URL update (UK) | image.storage.container.url.lifestyle.V1 https://media-uk.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnya / Vishal Jaiswal | Not Started
Hybris AppConfig | V2 URL update (US) | image.storage.container.url.lifestyle.V2 https://media-us.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnya / Vishal Jaiswal | Not Started
Hybris AppConfig | V3 URL update (Global) | image.storage.container.url.lifestyle.V3 https://media.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnya / Vishal Jaiswal | Not Started
Hybris AppConfig | V4 URL update (EA) | image.storage.container.url.lifestyle.V4 https://media-ea.landmarkshops.in/lifestyle/ → lifestyle-new/ | Jagnya / Vishal Jaiswal | Not Started
Redis Cache | Clear Redis cache for LS PDP | Clear Redis cache for LS PDP | Jagnya / Vishal Jaiswal | Not Started
Cloudflare Cache | Purge Cloudflare — PDP Static API | Purge all PDP static API responses to pick up new image URLs | Yeddulaharinath Reddy | Not Started
Unbxd Full feed | Unbxd Full feed | Unbxd Full feed | Savitha / support team
8. Sanity Check | Gift card images working | Verify gift card images load from lifestyle-new | QA Team | Not Started
8. Sanity Check | Elite product images working | Verify Elite product images load correctly | QA Team | Not Started
8. Sanity Check | Other assets (banners, icons) | Confirm non-product assets unaffected | QA Team | Not Started
9. Image Health | Run image health check script | python check-image-health.py --pages 0 --workers 100 Check broken_images.csv in image_health/ | Jagnya | Not Started
9. Image Health | Triage broken images | Review broken_images.csv; reprocess failed SKUs | Jagnya / Vishal Jaiswal | Not Started